## Gantt Chart
Task | Start Date | End Date | Duration (days) | May 6 | May 7 | May 8 | May 9 | May 10 | May 11 | May 12 | May 13 | May 14 | May 15 | May 16 | May 17 | May 18 | May 19 | May 20 | May 21 | May 22 | May 23 | May 24 | May 25 | May 26 | May 27 | May 28 | May 29 | May 30 | May 31 | June 1 | June 2 | June 3 | June 4 | June 5 | June 6 | June 7 | June 8 | June 9 | June 10 | June 11 | June 12 | June 13 | June 14 | June 15 | June 16 | June 17 | June 18 | June 19 | June 20 | June 21 | June 22 | June 23 | June 24 | June 25 | June 26 | June 27 | June 28 | June 29 | June 30
Define project scope | 2026-05-06 | 2026-05-07 | 2 | bar: May 6 to May 7
Identify stakeholders | 2026-05-08 | 2026-05-08 | 1 | bar: May 8
Assign team roles | 2026-05-09 | 2026-05-09 | 1 | bar: May 9
Create project timeline | 2026-05-10 | 2026-05-10 | 1 | bar: May 10
Research target users | 2026-05-11 | 2026-05-14 | 4 | bar: May 11 to May 14
Analyze competitor apps | 2026-05-11 | 2026-05-14 | 4 | bar: May 11 to May 14
Create user personas | 2026-05-15 | 2026-05-16 | 2 | bar: May 15 to May 16
Define user needs | 2026-05-17 | 2026-05-18 | 2 | bar: May 17 to May 18
Define core app features | 2026-05-19 | 2026-05-21 | 3 | bar: May 19 to May 21
Create user journey | 2026-05-22 | 2026-05-23 | 2 | bar: May 22 to May 23
Design UI/UX wireframes | 2026-05-24 | 2026-05-28 | 5 | bar: May 24 to May 28
Review prototype design | 2026-05-29 | 2026-05-30 | 2 | bar: May 29 to May 30
Design AI conversation flow | 2026-05-24 | 2026-05-27 | 4 | bar: May 24 to May 27
Build AI response system | 2026-05-28 | 2026-06-04 | 8 | bar: May 28 to June 4
Connect AI with backend | 2026-06-05 | 2026-06-07 | 3 | bar: June 5 to June 7
Test AI response quality | 2026-06-08 | 2026-06-10 | 3 | bar: June 8 to June 10
Build frontend prototype | 2026-05-31 | 2026-06-06 | 7 | bar: May 31 to June 6
Build backend structure | 2026-05-31 | 2026-06-06 | 7 | bar: May 31 to June 6
Connect database | 2026-06-07 | 2026-06-09 | 3 | bar: June 7 to June 9
Integrate full system | 2026-06-10 | 2026-06-13 | 4 | bar: June 10 to June 13
Recruit beta users | 2026-06-14 | 2026-06-15 | 2 | bar: June 14 to June 15
Conduct beta testing | 2026-06-16 | 2026-06-20 | 5 | bar: June 16 to June 20
Collect user feedback | 2026-06-21 | 2026-06-22 | 2 | bar: June 21 to June 22
Fix issues and improve product | 2026-06-23 | 2026-06-27 | 5 | bar: June 23 to June 27
Create launch messaging | 2026-06-20 | 2026-06-23 | 4 | bar: June 20 to June 23
Prepare social media content | 2026-06-24 | 2026-06-27 | 4 | bar: June 24 to June 27
Set up customer support process | 2026-06-24 | 2026-06-27 | 4 | bar: June 24 to June 27
MVP Launch | 2026-06-30 | 2026-06-30 | 1 | bar: June 30